## Agenda
2017-12-16
Meeting Agenda | Comments | Finalized
App Name - Suggestions/Finalization | Accompany, Companion, Buddy, Finding Buddy, etc. (Please suggest appropriate names for the App) Lets, Sea, Ocean, Zin, MTHREE, Getgo, Noia | Getgo, Zin,Zinda, Jeele, Lets, Sea,Noia (No one is alone)
App Logo designing samples | Maha can show them on screen if available (Common Repository needed to store the Logos)
Project Plan & Strategy, Roles and Responsibilities | Contingency Plan
Schedule and time lines
Resources + Infra Expenditures
Budget
Requirements discussion
Additions/Action Items
2017-12-30
Meeting Agenda | Comments
Decide the App Name | Zinvi Zinva Nizda Zinla Mizda Lyma (I made this one with letters of our names) Zinbar Prasti (Sanskrit for companion) Sahaya (Sanskrit for companionship) Zivat (Somali for company) Biru (Indonesian for blue) Zivot (Czech for life) Valkai (Tamil for life) - Nir/Neer (Tamil for water) - this one is very simple and gives a good theme for the app (colors, backgrounds...)
Talk about the Couples option to decide on the functionality
Design Finalization

## Action Items
Item | Comments | Responsible | Status | Target Date
React JS | Upskilling | Dev Team | In Progress | 2018-01-15
Repository Creation |  | Maha | In Progress | 2017-12-18
Contingency Plan |  | Mydeen |  | 2017-12-31
Logo Finalization and verification for uniqueness |  | Ajay |  | 2017-12-31
Advertisements in the App + Advertising of the App | Research | Miquel |  | 2018-01-20
Requirements Call |  | All 3 |  | 2017-12-23