## Sheet1
S.No | Particluars | Start Date | End Date | Responsibility | Status | Comments
1 | App name | 2017-12-05 | 2017-12-23 | Team | In Progress
2 | Domain registration | 2017-12-05 | 2017-12-23 | Maha | Not Started
3 | Logo Design | 2017-12-05 | 2017-12-31 | Maha | In Progress | Finalized a Logo (need to find if it exists)
4 | Page screenshot proto type | 2017-12-05 | 2017-12-31 | Maha | In Progress
5 | Requirements Doc | 2017-12-05 | 2017-12-15 | Mydeen | In Progress
6 | Client Design doc (TDD) | 2017-12-05 | 2017-12-31 | Mydeen/Maha | Not Started
7 | Server Design Doc | 2017-12-05 | 2018-01-15 | Maha | Not Started
8 | Database Design | 2017-12-05 | 2018-01-15 | Mydeen/Maha | Not Started
9 | Build Phase I | 2018-01-01 | 2018-03-31 | Mydeen/Maha | Not Started
10 | Testing - Developer Testing | 2018-03-01 | 2018-03-31 | Mydeen/Maha | Not Started
11 | Testing - Business Testing | 2018-03-20 | 2018-03-31 | Miquel | Not Started
12 | Build Phase II | 2018-04-01 | 2018-06-30 | Mydeen/Maha | Not Started
13 | Testing - Developer Testing | 2018-06-01 | 2018-06-30 | Mydeen/Maha | Not Started
14 | Testing - Business Testing | 2018-06-20 | 2018-06-30 | Miquel | Not Started
15 | Product release Phase1 - Alpha version | 2018-07-01 | 2018-07-01 | Team | Not Started
16 | Build Phase III | 2018-07-01 | 2018-09-30 | Mydeen/Maha | Not Started
17 | Testing - Developer Testing | 2018-09-01 | 2018-09-30 | Mydeen/Maha | Not Started
18 | Testing - Business Testing | 2018-09-20 | 2018-09-30 | Miquel | Not Started
19 | Product release Phase2 - Beta Version | 2018-10-01 | 2018-10-01 | Mydeen/Maha | Not Started
20 | Outstanding issue fixes | 2018-10-01 | 2018-10-15 | Team | Not Started
21 | Product release Phase3 - Version 1.0 | 2018-10-15 | 2018-10-15 | Team | Not Started