## Sheet1
S.No | Task | Task Owner | Start Date | Expected End Date | Actual End Date | Status | Comments
1 | Database Design - Initial Draft | Mydeen | 2017-12-30 | 2018-01-01 |  | In Progress
2 | Database Design - Reviewer | Maha | 2018-01-01 | 2018-01-01 |  | Not Started
3 | Database Design - Final Version | Mydeen | 2018-01-01 | 2018-01-02 |  | Not Started
4 | UI Design | Ajay | 2017-12-25 | 2018-01-02 |  | In Progress
5 | Requirements Doc Update based upon UI | Ajay | 2017-12-25 | 2018-01-04 |  | In Progress
6 | Verify the requirements against UI | Team | 2018-01-04 | 2018-01-06 |  | In Progress
7 | UI Corrections | Ajay | 2018-01-07 | 2018-01-08 |  | Not Started
8 | Verify the requirements against UI - Finalize Requirements | Team | 2018-01-08 | 2018-01-09 |  | Not Started
9 | Building Technical Design Document | Maha/Mydeen | 2018-01-10 | 2018-01-17 |  | Not Started
10 | Advertisement Research | Miquel | 2017-12-30 | 2018-01-10 |  | In Progress
11 | Technical Design Review | Team | 2018-01-18 | 2018-01-20 |  | Not Started
12 | Code Building - Phase I | Developers | 2018-01-22 | 2018-03-31 |  | Not Started
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53